## MI-GSI DATA TRACKING TABLE
Survey​​ | Location | MB Data Processing Complete (Y/N) | ARE DATA IN MI SERVER ? | ARE DATA IN GSI SERVER ? | Prelim Survey Folder | Final Updated Survey Leg returned from GSI | Leg Report Received | Status | Notes​
​2009 | [7 empty] | ​
IMAR09_Belmullet-Annagh | Belmullet-Annagh |  | Y | N - No data GSI | Y |  |  | ​Open | test2
KRY0902 |  | Y | Y | Y | Y |  |  | ​​​Closed
CV09_01_Final |  | Y | Y | Y | Y |  |  | ​​​Closed
CV09_02_Final |  | Y | Y | Y | Y |  |  | ​​​Closed
CV09_03_Final |  | Y | Y | Y | Y |  |  | ​​​Closed
CV09_05_Final |  | Y | Y | Y | Y |  |  | ​​​Closed
2010 | [7 empty] | ​
KRY10_01 | Dublin Bay | Y | Y |  |  | Y | ​Y | ​​​Closed
KRY10_02 | Kinsale | Y | Y |  |  | Y | Y | ​​​Closed
KRY10_03 |  | Y | Y |  |  |  |  | ​​​Closed
KRY10_04 | Blacksod | Y | Y |  |  | Y | N | ​​​Closed | survey report outstanding​
CV10_Nephrops | West of Aran Islands | Y | Y |  |  | Y | N | ​​​Closed | report outstanding​
CV10_01_Final |  | Y | Y |  |  |  |  | ​​​Closed
CV10_02_Final |  | Y | Y |  |  |  |  | ​​​Closed
CV10_03_Final |  | Y | Y |  |  |  |  | ​​​Closed
CV10_SEI_Final |  | Y | Y |  |  |  |  | ​​​Closed
2011 | [7 empty] | ​
Geo11_01 | Skerries | Y | Y |  |  | Y | N | ​​​Closed | survey report outstanding
GEO11_02 | Waterford | Y | Y |  |  | Y | N | ​​​Closed | survey report outstanding
GEO11_03 | Wexford | Y | Y |  |  |  |  | ​​​Closed | survey report outstanding
GEO11_04 | Achill | Y | N - No data in MI |  |  | Y | N | ​Open
GEO11_05 |  | N​ | Y - prelim |  |  |  |  | ​Open
GEO11_06 | Dundalk (InisHydro) | Y | Y |  |  | Y | N | ​​​Closed | survey report outstanding
KRY11_01 |  | Y | Y |  |  |  |  | ​​​Closed
KRY 11_02 | Wexford | Y | Y |  |  | Y | N | ​​​Closed | survey report outstanding
KRY11_03 |  | Y | Y |  |  |  |  | ​​​Closed
KRY11_04 |  | Y | Y |  |  |  | N | ​​​Closed | survey report outstanding
KRY11_05 |  | N​ | Y - prelim |  |  | Y | N | ​Open | survey report outstanding
KRY11_06 |  | Y | Y |  |  |  |  | ​​​Closed | survey report outstanding
SEAI_CV11_01_Belmullett_Final | Achill | Y | Y |  |  |  |  | ​​​Closed
SEAI_GEO11_04_Final |  | Y | Y |  |  |  |  | ​​​Closed
CV11_01_Final |  | Y | Y |  |  |  |  | ​​​Closed
CV11_02_Final |  | Y | Y |  |  |  |  | ​​​Closed
CV11_03_Final |  | Y | Y |  |  |  |  | ​​​Closed
CV11_INIS-HYDRO_Final |  | Y | Y |  |  |  |  | ​​​Closed
2012 | [7 empty] | ​
KRY12_01 | Dundalk (InisHydro) | Y | Y |  |  | Y | N | ​Closed | report outstanding
KRY12_02 |  | Y | Y |  |  |  |  | ​Closed
KRY12_03 |  | Y | Y |  |  |  |  | ​Closed
KRY12_04 |  | N​ | N |  |  |  |  | ​Closed | ignore
KRY12_05 |  | Y | N - Missing raw data |  |  | Y | N | ​Open | report outstanding
GEO12_01 | Dundalk (InisHydro) | Y | Y |  |  | Y | N | ​Closed | report outstanding
GEO12_02 | Inishbofin | Y | Y |  |  | Y | N | ​Closed | report outstanding
GEO12_03 |  | N​ | N - No data in MI |  |  | Y | N | ​Open
GEO12_04 | Cork | Y | Y |  |  | Y | N | ​Closed | report outstanding
CB12_01 | Cork | Y | Y |  |  | Y | N | ​Closed | report outstanding
CV12_01_Final |  | Y | Y |  |  |  |  | ​Closed
CV12_02_Final |  | Y | Y |  |  |  |  | ​Closed
CV12_03_Final |  | Y | Y |  |  |  |  | ​Closed
CV12_SEAI_Final |  | Y | Y |  |  |  |  | ​Closed
CV12_SEAI_Galway_Final |  | Y | Y |  |  |  |  | ​Closed
CV12_SEAI_SEP27_Clare_Final |  | Y | Y |  |  |  |  | ​Closed
2013 | [7 empty] | ​
CB13_01 | Dublin - Lambay/Skerries | Y | Y |  | Y |  |  | ​Closed
CB13_02 | Louth/InisHydro | Y | Y |  |  | Y | N | ​Closed | report outstanding
CB13_03 | Kerry/Dingle | Y | Y |  |  | Y | N | ​Closed | report outstanding
CB13_04 | Shannon | Y | Y |  |  | Y | Y | ​Closed | report outstanding
CB13_05 |  | Y | Y |  |  |  |  | ​Closed | report outstanding
GEO13_01 | Dublin - Lambay/Skerries | Y | Y |  |  | Y | N | ​Closed | report outstanding
GEO13_02 | Louth/InisHydro | Y | Y |  |  | Y | N | ​Closed | report outstanding
GEO13_03 | Kerry/Dingle | Y | Y |  |  | Y | N | ​Closed | report outstanding
GEO13_04 | Castletownbere | Y | Y |  |  | Y | N | ​Closed | report outstanding
GEO13_05 |  | Y | Y |  |  |  |  | ​Closed
KRY13_03 | Cork/Fastnet | Y | Y |  |  | Y | Y | ​Closed | report outstanding
KRY13_04 | Kerry/Dingle | Y | Y |  |  | Y | N | ​Closed | report outstanding​
KRY13_05 |  | Y | Y |  |  |  |  | ​Closed
CV13_01 |  | Y | Y |  |  |  |  | ​Closed
CV13_02 |  | Y | Y |  |  |  |  | ​Closed
CV13_ARAN_ISLANDS_Final |  | Y | Y |  |  |  |  | ​Closed
CV13_SEAI_1_Final |  | Y | Y |  |  |  |  | ​Closed
CV13_SEAI_2_Final |  | Y | Y |  |  |  |  | ​Closed
CV13_SEAI_3_Final |  | Y | Y |  |  |  |  | ​Closed
CV13_SEAI_4_Final |  | Y | Y |  |  |  |  | ​Closed
2014 | [7 empty] | ​
CB14_01 | Swilly/Foyle | Y | Y |  |  | Y | N | ​Closed | report outstanding
CB14_02 |  | Y | Y |  |  |  |  | ​Closed
CB14_03 | Broadhaven | Y | Y |  |  | Y | N | ​Closed | report outstanding
CB14_04 | Killary | Y | Y |  |  | Y | N | ​Closed | report outstanding
CB14_05 | Tralee | Y | Y |  |  | Y | Y | ​Closed | report outstanding
CB14_06 | Boyne | Y | Y |  |  | Y | N | ​Closed | report outstanding
GEO14_01 | Broadhaven | Y | Y |  |  | Y | N | ​Closed | report outstanding
GEO14_02 | Killary | Y | Y |  |  | Y | N | ​Closed | report outstanding
GEO14_03 | Tralee | Y | Y |  |  | Y | Y | ​Closed | report outstanding​
GEO14_04 | Boyne | Y | Y |  |  | Y | N | ​Closed | report outstanding​
KRY14_01 | Swilly/Foyle | Y | Y |  |  | Y | N | ​Closed | report outstanding
KRY14_02 |  | Y | Y |  |  |  | N | ​Closed | report outstanding
KRY14_03 | Broadhaven | Y | Y |  |  | Y | N | ​Closed | report outstanding
KRY14_04 | Killary | Y | Y |  |  | Y | N | ​Closed | ​report outstanding
KRY14_05 | Tralee | Y | Y |  |  |  | N | ​Closed | ​report outstanding
KRY14_06 | Foyle | Y | Y |  |  | Y | N | ​Closed | report outstanding
CV14_01 | Galway | Y | Y |  |  | Y | Y | ​Closed
CV14_02 | Galway/Tralee | Y | Y |  |  | Y | Y | ​Closed
CV14_03 | Cork | Y | Y |  |  | Y | Y | ​Closed
CV14_SEAI1 | West Clare | Y | Y |  |  | Y | Y | ​Closed
2015 | [7 empty] | ​
GEO15_01 | Bannow | Y | Y |  |  | Y | N | ​Closed | report outstanding
GEO15_02 | Youghal/Dungarvan | Y | Y |  |  | Y | N | ​Closed | report outstanding
GEO15_03 | Wexford | Y | Y |  |  | Y | N | ​Closed | report outstanding​
GEO15_04 | Boyne | Y | Y - prelim |  | Y |  |  | ​Open | ship dataset recieved
GEO15_05 | Carlingford Lough | N​ | Y - prelim |  |  | Y | N | ​Open | ship dataset recieved
TON15_01 | Bannow | Y | Y |  |  | Y | N | ​Closed | report outstanding
TON15_02 | Youghal/Dungarvan | Y | Y |  |  | Y | N | ​Closed | report outstanding
TON15_03 | Wexford | Y | Y |  |  | Y | N | ​Closed | report outstanding​
TON15_04 | Boyne | Y | Y - prelim |  | Y |  |  | ​Open | ship dataset recieved
TON15_05 | Carlingford Lough | N​ | Y - prelim |  |  | Y | N | ​Open | ship dataset recieved
KRY15_01 | Bannow | Y | Y |  |  | Y | N | ​Closed | report outstanding
KRY15_02 | Youghal/Dungarvan | Y | Y |  |  | Y | N | ​Closed | report outstanding
KRY15_03 | Wexford | Y | Y |  |  | Y | N | ​Closed | report outstanding​
KRY15_04 | Boyne | N​ | Y - prelim |  | Y |  |  | ​Open | ship dataset recieved
KRY15_05 | Foyle | Y | Y |  |  |  |  | ​Closed | report outstanding
2016 | [7 empty] | ​
​Geo16_01 | Wicklow​ | Y | Y |  |  |  |  | ​Closed
​Geo16_02 | Wicklow​ | Y | Y |  | ​Y |  |  | ​Closed | report outstanding
​Geo16_03 | Wicklow/Wexford​ | Y | Y |  | ​Y |  |  | ​Closed | report outstanding
​Geo16_04 | Kenmare​ | Y | Y |  | ​Y |  |  | ​Closed | report outstanding
​KRY16_01 | ​Wicklow | Y | Y |  |  | Y | N | ​Closed | report outstanding
​Kry16_02 | Wicklow​ | Y | Y |  |  |  |  | ​Closed | report outstanding
​Kry16_03 | Wicklow/Wexford​ | Y | Y |  |  |  |  | ​Closed | report outstanding
​Ton16_01 | Wicklow​ | Y | Y |  |  |  |  | ​Closed | ship dataset recieved
​Ton16_02 | Wicklow​ | N​ | Y - prelim |  | Y |  |  | ​Open | ship dataset recieved
​Ton16_03 | Wexford​ | Y | Y |  |  |  |  | ​Closed | ship dataset recieved
​CLN16_01 | Irish Sea​ | Y | N - No data in MI |  | Y |  |  | ​Open
CE16_01 |  | Y | Y |  |  |  |  | ​Closed
CV16_01 |  | Y | Y |  |  |  |  | ​Closed
CV16_02 |  | Y | Y |  |  |  |  | ​Closed
CV16_03 |  | Y | Y |  |  |  |  | ​Closed
CV16_04 |  | Y | Y |  |  |  |  | ​Closed
CV16_05 |  | Y | Y |  |  |  |  | ​Closed
2017 | [7 empty] | ​
Geo17_01 | Skerries | Y | Y |  |  | ​ | ​ | ​Closed | report outstanding​
​Geo17_02 | ​Rosslare | N​ | ​ |  | ​Y | ​ | ​ | Open | ship dataset recieved
Geo17_03 |  | Y | Y |  |  |  |  | ​Closed | report outstanding​
​KRY17_01 | ​Skerries | Y | Y |  |  | ​ | ​ | ​Closed | report outstanding​
Kry17_02 | Rosslare | N​ | ​ |  | ​Y | ​ | ​ | Open | ship dataset recieved
​Lir17_01 | Rosslare | Y | Y |  | ​Y | ​ | ​ | ​Closed | report outstanding​
​Lir17_02 |  | Y | Y |  | Y |  |  | ​Closed | report outstanding​
MAL17_01 | Wexford | Y | Y |  |  |  |  | ​Closed | report outstanding​
CE17_01 |  | Y | Y |  |  |  |  | ​Closed
CE17_02 |  | Y | Y |  |  |  |  | ​Closed
CV17_01_Final |  | Y | Y |  |  |  |  | ​Closed
CV17_02_Final |  | Y | Y |  |  |  |  | ​Closed
CV17_03_Final |  | Y | Y |  |  |  |  | ​Closed
CV17_04_Final |  | Y | Y |  |  |  |  | ​Closed
2018
KRY18_01 |  | N​ | N - No data in MI |  |  |  |  | Open
KRY18_02 |  | N​ | N - No data in MI |  |  |  |  | Open
KRY18_03 |  | N​ | N - No data in MI |  |  |  |  | Open
KRY18_04 |  | N​ | N - No data in MI |  |  |  |  | Open
MAL18_01 |  | N​ | N - No data in MI |  |  |  |  | Open
MAL18_02 |  | N​ | N - No data in MI |  |  |  |  | Open
LIR18_01 |  | N​ | N - No data in MI |  |  |  |  | Open
LIR18_02 |  | N​ | N - No data in MI |  |  |  |  | Open
LIR18_02 |  | N​ | N - No data in MI |  |  |  |  | Open
GEO18_01 |  | N​ | N - No data in MI |  |  |  |  | Open
GEO18_02 |  | N​ | N - No data in MI |  |  |  |  | Open
COR18_01 (AFBI) |  | N​ | N - No data in MI |  |  |  |  | Open
CE18_01 |  | Y | Y |  |  |  |  | Closed
CV18_01 |  | Y | Y |  |  |  |  | Closed
CV18_02 |  | Y | Y |  |  |  |  | Open
CV18_03 |  | N​ | Y |  |  |  |  | Open